## Sheet1
Date | # Hours | Tasks
2021-01-13 | 2 | Outlined flow of application; created an empty project; added a bottom navigation bar on home screen |  |  | Time | Total
2021-01-18 | 2.25 | Added icons to bottom nav bar; have a temporary theme; created the fragements for the nav bar |  | Week1 | 2 | 132.75 | APP
2021-01-19 | 2.5 | I needed activities not fragments;better formated bottom nav bar; actual navigation with java |  | Week2 | 7 |  | DATABASE
2021-01-20 | 2.25 | I worked on the add page;I learned some layouts and inputs;currently ruff and needs work |  | Week3 | 14.25
2021-01-25 | 6 | Finished with add/remove page layouts;working on search and settings next, then database |  | Week4 | 6
2021-01-26 | 4 | Played with themes; search screen looks good; button for barcode scan; next is camera implement; went back to fragments; settings layout started |  | Week5 | 3
2021-01-27 | 4.25 | refined the layouts; read about databases; active icons for navigation bar; started with barcode scanner; issue with null imagebutton |  | Week6 | 4.75
2021-02-01 | 1 | finished reading about databases; think I will use a MySQL server and a SQLite for local storage |  | Week7 | 3.25
2021-02-02 | 5 | resolved the camera issues; created a database structure | Break | Week8 | 0
2021-02-08 | 1 | resolved emulator issues; started login screen |  | Week9 | 18
2021-02-10 | 2 | learning MySQL; some issues with installation |  | Week10 | 15.25
2021-02-17 | 3 | setup the database on the pc that will run the server; created some of the tables |  | Week11 | 18.5
2021-02-18 | 1.75 | finished tables and testing inserts; will need to work on storing passwords |  | Week12 | 4
2021-02-22 | 1 | connecting database to the application; after some research I need a web server |  | Week13 | 14.25
2021-02-23 | 2.25 | lots of issues with databases; changed to phpmyadmin |  | Week14 | 13
2021-03-08 | 1 | worked on web part for database |  | Week15 | 9.5
2021-03-09 | 8 | added more to the php files; can now add from the application; need to work on async
2021-03-10 | 2 | fixed async; nearly done with adding process (not completely)
2021-03-11 | 7 | item screen now has location spinner; error catching; adding new items done; need to work on fragment stack; issue with hardware device
2021-03-16 | 2.5 | no double entries; update fragment; update php; fixed update php; moved php files into folders; secured config file
2021-03-17 | 5.25 | db has issue with pma user; home fragment has listview; remove nearly finsihed; need way to pass quantity based on location
2021-03-18 | 7.5 | remove screen w/custom request; cleaned up remove with functions; dialog for errors; quantity limit based on location; need to fix the php for
2021-03-22 | 2.75 | Removing an item done; public method for fragment transition; change add fragment
2021-03-23 | 8 | search fragment buttons; public spinner; auto search with listview works; fix remove array parse; auto search done; manual set up; fix some phP
2021-03-24 | 7.75 | finish addauto php issue; fixing php prepared statements; all php done; add screens utilize functions; manual search screen;
2021-03-30 | 4 | fix php issues; images work for most screens;
2021-04-04 | 2.25 | images for all screens; login screen fixes
2021-04-06 | 6.5 | SQLite implemented; autocomplete WIP; loaded on hardware device; found some issues
2021-04-07 | 2 | worked on camera issues, not done; fixed adding new item issue
2021-04-08 | 3.5 | Login finished withg password hashing
2021-04-12 | 2 | Clean up functions
2021-04-13 | 6 | Found error with adding items where duplicate items could be added
2021-04-14 | 5 | Found error with images being rotated; tried many things but could not get it to work on the hardware device
2021-04-19 | 2 | Add register screen and completed php for it
2021-04-20 | 2 | Tried to change theme in settings
2021-04-21 | 3 | Still confused how to add themes to whole app with switch; attempted to change colors
2021-04-29 | 2.5 | Wrap up loose ends; add the tutorial to the readme; add all files to github